## Sprint Planner
🚀 RakshAI MVP — Sprint Planner ¦ July 3 – July 30, 2026
🔵 You (Lead Dev) ¦ 🟣 Yadnyesh (Frontend) ¦ 🟢 Riddhi (Frontend) ¦ Status → ⬜ To Do 🟡 In Progress 🟩 Done 🔴 Blocked
# | Task | Assigned to | Week | Dates | Phase | Status | Acceptance criteria / notes
WEEK 1 • Jul 3–9
1 | Repo setup: Next.js 14 + Tailwind + shadcn/ui + Vercel deploy | You | Week 1 | Jul 3 | Setup | To Do | Push to GitHub. Share repo link with interns. Confirm Vercel preview URL works.
2 | Prisma schema: User, Vendor, NDA, Questionnaire, RiskSummary tables | You | Week 1 | Jul 3–4 | Setup | To Do | Run migrations against Neon DB. Seed 5 dummy vendors. Share schema.prisma with team.
3 | NextAuth.js: dual-role auth (BUYER / VENDOR) + route guards | You | Week 1 | Jul 4–5 | Setup | To Do | BUYER role sees /buyer/*, VENDOR role sees /vendor/*. Unauthenticated redirects to /login.
4 | Login page + Register page (both roles) | Yadnyesh | Week 1 | Jul 3–5 | Phase 2 | To Do | Use shadcn/ui Form. Role selector on register (Buyer / Vendor). Shows validation errors.
5 | Buyer dashboard shell: sidebar nav + vendor data table (static) | Riddhi | Week 1 | Jul 3–5 | Phase 1 | To Do | Table shows: Vendor Name, Risk Tier badge, AI Exposure %, Status chip, Last Updated.
6 | Vendor CRUD API routes (GET /vendors, POST, PATCH) | You | Week 1 | Jul 5 | Phase 1 | To Do | Return JSON. Validate with Zod. Test with Postman / curl before handing off.
7 | Connect vendor table to real API + add loading skeleton | Riddhi | Week 1 | Jul 5–6 | Phase 1 | To Do | Fetch from /api/vendors. Show shadcn Skeleton while loading. Handle empty state.
WEEK 2 • Jul 10–16
8 | CSV import endpoint for vendor bulk upload | You | Week 2 | Jul 7–8 | Phase 1 | To Do | POST /api/vendors/import. Accept .csv, parse, upsert vendors. Return success count + errors.
9 | Vendor invite flow: generate invite link → send email | You | Week 2 | Jul 8–9 | Phase 2 | To Do | Generate unique token. Store in DB. Email via Resend/Nodemailer. Token expires in 7 days.
10 | NDA acceptance page + timestamp recording | Yadnyesh | Week 2 | Jul 7–9 | Phase 2 | To Do | Show NDA text. Checkbox + 'Accept & Continue' button. Write accepted_at to DB on submit.
11 | Route guard: block vendor access until NDA signed | You | Week 2 | Jul 9 | Phase 2 | To Do | Middleware: if vendor.nda_accepted = false → redirect to /vendor/onboard. No bypass.
12 | Questionnaire form UI (4 sections, dynamic fields) | Riddhi | Week 2 | Jul 7–11 | Phase 3 | To Do | Sections: Company Info, Security Posture, AI Tools Used, Compliance. shadcn/ui form. Save draft on each section.
13 | Questionnaire save/submit API + status update | You | Week 2 | Jul 10–11 | Phase 3 | To Do | POST /api/questionnaire. Save answers. On submit set vendor.status = 'PENDING_REVIEW'.
14 | Vendor portal navigation (dashboard + questionnaire status) | Yadnyesh | Week 2 | Jul 10–11 | Phase 3 | To Do | Vendor sees: NDA status, questionnaire progress bar, submission confirmation.
WEEK 3 • Jul 17–23
15 | Claude API integration + risk summary prompt engineering | You | Week 3 | Jul 14–15 | Phase 3 (AI) | To Do | Spend full day on prompt. Test 10 questionnaire responses. Summary must: list top 3 risks, flag gaps, give tier (Low/Med/High/Critical).
16 | Streaming risk summary API endpoint | You | Week 3 | Jul 15–16 | Phase 3 (AI) | To Do | POST /api/risk-summary/[vendorId]. Stream Claude response using Vercel AI SDK. Store final text in DB.
17 | Risk summary review page (buyer side) | Yadnyesh | Week 3 | Jul 14–17 | Phase 3 (AI) | To Do | Show: AI-generated summary, risk tier badge, gap list. Streaming text animation while generating.
18 | Approve / Request remediation flow | Riddhi | Week 3 | Jul 14–17 | Phase 3 (AI) | To Do | Two buttons: 'Approve vendor' and 'Request remediation'. Modal for remediation note. Update vendor.status.
19 | Vendor status updates (approved / pending / remediation required) | You | Week 3 | Jul 17 | Phase 3 (AI) | To Do | Status changes reflected on buyer dashboard in real time (or on refresh). Email notification to vendor.
20 | Vendor detail page (/buyer/vendors/[id]) | Yadnyesh | Week 3 | Jul 17–18 | Phase 3 (AI) | To Do | Show: full profile, questionnaire answers, AI risk summary, approval history, current status.
WEEK 4 • Jul 24–30
21 | Monitoring dashboard with seeded charts (Phase 5 stub) | Riddhi | Week 4 | Jul 21–23 | Phase 5 (stub) | To Do | Recharts line chart: risk score over time. Pie: vendors by tier. Table: top 5 open action items. All seeded data.
22 | 'Coming soon' locked states for Phases 4, 6, 7, 8 | Yadnyesh | Week 4 | Jul 21–22 | Roadmap | To Do | Show phase names in nav with a lock icon and 'Coming soon' tooltip. No broken links.
23 | Seed realistic demo data (3 vendors in different states) | You | Week 4 | Jul 22–23 | Demo prep | To Do | Vendor 1: approved + AI summary. Vendor 2: pending review. Vendor 3: remediation requested. All look real.
24 | Full end-to-end flow testing (buyer + vendor paths) | You | Week 4 | Jul 23–24 | QA | To Do | Run through: invite → NDA → questionnaire → AI summary → approve. Fix any broken steps.
25 | UI polish pass: spacing, typography, mobile responsive | Yadnyesh | Week 4 | Jul 24–25 | Polish | To Do | No overflowing text. Cards consistent height. Works on 375px mobile. Check dark/light if applicable.
26 | Error handling + empty states across all pages | Riddhi | Week 4 | Jul 23–25 | Polish | To Do | Every page has an empty state. API errors show toast, not blank screen. Loading skeletons everywhere.
27 | Final Vercel deploy + custom domain + QA | You | Week 4 | Jul 28–30 | Ship | To Do | Production deploy. Test on production URL. Share login credentials doc with the client.
28 | Demo script + walkthrough prep | You | Week 4 | Jul 29–30 | Ship | To Do | Write bullet-point demo script. Pre-login as buyer and vendor in different browsers. Rehearse once.

## Intern A — Tasks
🟣 Yadnyesh — Task Board ¦ RakshAI MVP
Update 'Status' as you work. Ask questions in standup. Never be blocked silently — message the lead dev immediately.
# | Task description | Week | Due by | Status | How you know it's done
1 | Login page + Register page (both roles) | Week 1 | Jul 5 | To Do | shadcn/ui Form. Role selector. Validation errors show inline.
2 | NDA acceptance page + timestamp recording | Week 2 | Jul 9 | To Do | Checkbox + button. accepted_at stored in DB. Confirmed by lead dev.
3 | Vendor portal navigation (dashboard + questionnaire status) | Week 2 | Jul 11 | To Do | Vendor sees NDA status, questionnaire progress bar, submission confirmation screen.
4 | Risk summary review page (buyer side) | Week 3 | Jul 17 | To Do | Streaming text shows while Claude generates. Risk tier badge visible. Looks polished.
5 | Vendor detail page (/buyer/vendors/[id]) | Week 3 | Jul 18 | To Do | Shows: profile, questionnaire answers, AI summary, approval history, current status.
6 | 'Coming soon' locked states for Phases 4, 6, 7, 8 | Week 4 | Jul 22 | To Do | Lock icon + tooltip on each phase. No broken links. Looks intentional, not broken.
7 | UI polish pass: spacing, typography, mobile responsive | Week 4 | Jul 25 | To Do | No overflow text. Cards consistent. Works on 375px screen. Lead dev signs off.

## Intern B — Tasks
🟢 Riddhi — Task Board ¦ RakshAI MVP
Update 'Status' as you work. Ask questions in standup. Never be blocked silently — message the lead dev immediately.
# | Task description | Week | Due by | Status | How you know it's done
1 | Buyer dashboard shell: sidebar nav + vendor data table (static) | Week 1 | Jul 5 | To Do | Table shows: Vendor Name, Risk Tier badge, AI Exposure %, Status chip, Last Updated.
2 | Connect vendor table to real API + loading skeleton | Week 1 | Jul 6 | To Do | Fetches live from /api/vendors. Skeleton shows while loading. Empty state if no vendors.
3 | Questionnaire form UI (4 sections, dynamic fields) | Week 2 | Jul 11 | To Do | 4 sections complete. Saves draft per section. Submit button available only after all sections done.
4 | Approve / Request remediation flow | Week 3 | Jul 17 | To Do | Two buttons work. Remediation note modal saves. Vendor status updates visible on buyer dashboard.
5 | Monitoring dashboard with seeded charts (Phase 5 stub) | Week 4 | Jul 23 | To Do | Line chart (risk over time), pie chart (vendors by tier), top 5 action items table — all look real.
6 | Error handling + empty states across all pages | Week 4 | Jul 25 | To Do | No blank screens on API error. Every list page has an empty state illustration + message.

## Daily Standup Log
📋 Daily Standup Log — RakshAI MVP ¦ Fill this in every day at standup (10 min max)
Date | Who | Done yesterday | Doing today | Blockers
Jul 03 | You (Lead)
Jul 03 | Yadnyesh
Jul 03 | Riddhi
Jul 06 | You (Lead)
Jul 06 | Yadnyesh
Jul 06 | Riddhi
Jul 07 | You (Lead)
Jul 07 | Yadnyesh
Jul 07 | Riddhi
Jul 08 | You (Lead)
Jul 08 | Yadnyesh
Jul 08 | Riddhi
Jul 09 | You (Lead)
Jul 09 | Yadnyesh
Jul 09 | Riddhi
Jul 10 | You (Lead)
Jul 10 | Yadnyesh
Jul 10 | Riddhi
Jul 13 | You (Lead)
Jul 13 | Yadnyesh
Jul 13 | Riddhi
Jul 14 | You (Lead)
Jul 14 | Yadnyesh
Jul 14 | Riddhi
Jul 15 | You (Lead)
Jul 15 | Yadnyesh
Jul 15 | Riddhi
Jul 16 | You (Lead)
Jul 16 | Yadnyesh
Jul 16 | Riddhi
Jul 17 | You (Lead)
Jul 17 | Yadnyesh
Jul 17 | Riddhi
Jul 20 | You (Lead)
Jul 20 | Yadnyesh
Jul 20 | Riddhi
Jul 21 | You (Lead)
Jul 21 | Yadnyesh
Jul 21 | Riddhi
Jul 22 | You (Lead)
Jul 22 | Yadnyesh
Jul 22 | Riddhi

## Progress Tracker
📊 Progress Tracker — Update weekly
Weekly task completion
| Week 1 | Week 2 | Week 3 | Week 4
You (Lead Dev)
Yadnyesh
Riddhi
Team Total
Milestone checklist
Jul 5 | ✅ Auth + buyer dashboard working |  |  | [ ] complete
Jul 11 | ✅ Vendor portal + NDA flow complete |  |  | [ ] complete
Jul 18 | ✅ AI risk summary generating correctly |  |  | [ ] complete
Jul 23 | ✅ Full end-to-end flow tested |  |  | [ ] complete
Jul 25 | ✅ Monitoring dashboard seeded |  |  | [ ] complete
Jul 28 | ✅ UI polish done, deployed to Vercel |  |  | [ ] complete
Jul 30 | 🚀 MVP demo ready |  |  | [ ] complete